## Revision
Demoblaze Test Report
Version: 1.0
Revision History
Date | Version | Description | Author
2020-12-19 | 1.0 | Initial Draft | Monem Tajwer

## Project Info
Demoblaze Test Report
Version: 1.0
Project Information
Project Name | Demoblaze Ecom
Description | Test the ecommerce function of the "Demoblaze"
Issue Date: | 2020-12-19
Owner: | Monem Tajwer
Author: | Monem Tajwer
Location:
Reviewer information | Name | Department | Position
| N/A | N/A | N/A
Approver information

## Content
Test Report
Test Cycle | System Test
EXECUTED | PASSED |  |  | 0
| FAILED |  |  | 5
| (Total) TESTS EXECUTED (PASSED + FAILED) |  |  |  | 5
PENDING |  |  |  |  | 73
IN PROGRESS |  |  |  |  | 0 |  |  | Defect fixed | Not fixed
BLOCKED |  |  |  |  | 0 |  |  | 22 | 0
(Sub-Total) TEST PLANNED |  |  |  |  | 78
(PENDING + IN PROGRESS + BLOCKED + TEST EXECUTED)
Functions | Description | % TCs Executed | % TCs Passed | TCs pending | Priority | Remarks | Number of defects | Line of code (LOC) | Defect fixed
Login | Login with valid cred | 1% | 0% | 7 | High |  | 1 | 50 | 0
Signup/registration | Sign up with valid info | 0% | 0% | 16 | High |  | 0 | 100 | 0
User Account | Individual customer account | 1% | 0% | 11 | High |  | 1 | 60 | 0
Online Payment | Online card pyment for transaction | 1% | 0% | 3 | High |  | 1 | 300 | 0
Product | Proudct with details | 0% | 0% | 7 | High |  | 0 | 300 | 0
Cart | Product cart for track | 1% | 0% | 6 | High |  | 1 | 400 | 0
Search | Search product | 1% | 0% | 5 |  |  | 1 | 1500 | 0
Language | language support | 0% | 0% | 2 | High |  | 0 | 350 | 0
Purchase Tracking | Product tracking after purcahse | 0% | 0% | 5 | High |  | 0 | 1000 | 0
Category | Category for products | 0% | 0% | 7 | High |  | 0 | 1200 | 0
Wishlist | Wishlist for porducts | 0% | 0% | 3 | High |  | 0 | 1200 | 0